## Instructions
Agentic AI Use Case Feasibility Evaluation
A structured framework for IT leaders to evaluate whether a proposed agentic AI use case is worth pursuing
HOW TO USE THIS WORKBOOK
1. Complete the Use Case Canvas tab — if you cannot fill in every field, the use case is not well enough defined to evaluate.
2. Score all questions on the Assessment tab (1–5 scale) using the rubrics provided. Yellow cells are your input areas.
3. Complete the Hard Gates tab — any single 'Fail' is an automatic blocker regardless of score.
4. Fill in the Financial Model tab with real numbers.
5. Define success criteria on the Success Criteria tab before implementation begins.
6. Review the Scorecard tab — it calculates your composite score and recommendation automatically.
SCORING SCALE
1 = Significant gap / high risk / no evidence
2 = Partial / emerging / rough estimates only
3 = Adequate / moderate / reasonable basis
4 = Strong / solid evidence / well-positioned
5 = Excellent / proven / compelling
DIMENSION WEIGHTS
Strategic & Business Alignment: 25% — No business need = no project
Process Readiness: 15% — Garbage process in = garbage agent out
Technical Feasibility: 20% — Must be buildable
Risk, Governance & Compliance: 15% — Must be safe and legal (reverse-scored: higher = lower risk)
Financial Viability: 15% — Must be fundable and worth it
Organizational Readiness: 10% — Must be adoptable
COMPOSITE SCORE INTERPRETATION
4.0–5.0 STRONG GO — Proceed to funded pilot
3.0–3.9 CONDITIONAL GO — Proceed with mitigation plan for weak dimensions
2.0–2.9 NOT READY — Invest in readiness before re-evaluating
1.0–1.9 NO GO — Fundamental misalignment; redirect effort
COLOR LEGEND
Yellow cells = your input areas (scores, text, Pass/Fail)
Blue text = input values (financial model)
Gray cells = auto-calculated (do not edit)

## Use Case Canvas
USE CASE CANVAS
USE CASE IDENTITY
Use case name
Sponsoring business unit
Executive sponsor (name and title)
Problem statement (one sentence: who has what problem, and the consequence of not solving it)
Proposed agentic solution (one sentence: what would the agent do, using what tools, with what autonomy)
CURRENT STATE
How is this work done today?
How many people are involved? (FTEs)
Current volume (transactions/day, tickets/week, etc.)
Current end-to-end cycle time (per unit of work)
Current error/rework rate (%)
Annual fully loaded cost of this work today ($)
Known pain points
PROPOSED AGENT BEHAVIOR
What systems would the agent READ from?
What systems would the agent WRITE to or act in?
What tools would the agent use? (APIs, databases, email, ticketing, etc.)
What decisions would the agent make AUTONOMOUSLY?
What decisions require HUMAN APPROVAL before the agent acts?
What happens when the agent encounters something it cannot handle?
Who is the human in the loop, and what is their role?
What is the expected autonomy level? (Copilot / Semi-autonomous / Fully autonomous)

## Assessment
AGENTIC AI USE CASE — FEASIBILITY ASSESSMENT
# | Assessment Question | Score (1–5) | Evidence / Notes
D1: Strategic & Business Alignment (Weight: 25%)
Does this use case solve a meaningful business problem that leadership cares about, and is the timing right?
Rubric: 1=No clear business alignment; solution looking for a problem ¦ 2=Loosely related to a business goal but not a priority ¦ 3=Supports a recognized business need; moderate executive interest ¦ 4=Directly tied to a strategic priority; active executive sponsorship ¦ 5=Mission-critical alignment; executive urgency; clear competitive impact
1 | Does this use case directly support a stated strategic priority, OKR, or executive mandate?
2 | Is the business problem significant enough that solving it would be noticed by customers, revenue, or operational leadership — not just IT?
3 | Is there a named executive sponsor with budget authority who is actively championing this use case?
4 | Is the timing right — is the organization ready to absorb this change now, or are competing initiatives likely to starve it of attention?
5 | Does this use case create a competitive advantage, or does it prevent a competitive disadvantage?
6 | Is the use case scoped narrowly enough to deliver value in a defined timeframe (ideally under 90 days for a pilot)?
7 | If successful, does this use case create a reusable pattern or capability that could be applied to adjacent processes?
8 | Has the cost of inaction been articulated — growing backlog, competitive erosion, compliance risk, or employee turnover?
| D1 DIMENSION AVERAGE | —
D2: Process Readiness (Weight: 15%)
Is the underlying process well enough understood, documented, and measured to be a good candidate for agentic automation?
Rubric: 1=Process is undocumented, unstandardized, and heavily judgment-dependent ¦ 2=Partially documented; significant tribal knowledge; inconsistent execution ¦ 3=Documented and mostly standardized; some edge cases require human judgment ¦ 4=Well-documented, standardized, and measurable; most decisions are rule-based ¦ 5=Highly structured, fully instrumented, and almost entirely rule-based with clear exception paths
1 | Is the current process documented with clear steps, decision points, inputs, outputs, and exception paths?
2 | Are the business rules that govern decisions in this process explicit, codifiable, and stable — or are they tacit, judgment-heavy, and constantly changing?
3 | Is the process standardized across teams and locations, or does each group do it differently?
4 | Is the volume of work high enough and repetitive enough to justify the investment in an agentic solution?
5 | Are the inputs to this process structured (data fields, forms, APIs) or unstructured (free-text emails, scanned documents, verbal instructions)?
6 | What is the consequence of an error? (Low: rework an internal report. High: financial loss, regulatory violation, customer harm.)
7 | Is the current process already instrumented with metrics (cycle time, throughput, error rate, cost per transaction) that would serve as a baseline?
8 | Can the process be decomposed into a sequence of discrete, testable steps — or is it a single monolithic judgment call?
9 | Are process inputs and outputs well-defined enough that an agent's work can be objectively verified against expected results?
| D2 DIMENSION AVERAGE | —
D3: Technical Feasibility (Weight: 20%)
Can the organization actually build, deploy, and operate this agentic solution with available or obtainable technology, data, and skills?
Rubric: 1=Major technical blockers; required data/systems are inaccessible; no relevant skills in-house ¦ 2=Significant gaps in data, integration, or skills that would require 6+ months of pre-work ¦ 3=Feasible with moderate effort; some integration work needed; skills available or trainable ¦ 4=Strong technical foundation; APIs available; data is good; team has relevant experience ¦ 5=Technically straightforward; proven in POC; team has built similar systems before
1 | Are the data sources the agent needs accessible via APIs, databases, or file systems — with appropriate permissions and acceptable latency?
2 | Is the data clean, consistent, and complete enough to support reliable decision-making — or will significant remediation be needed first?
3 | Do the target systems the agent will write to or act in support programmatic interaction (APIs, webhooks, RPA hooks)?
4 | Can the agent's actions be constrained with guardrails (scope limits, approval gates, rollback capabilities, rate limits)?
5 | Is the LLM or AI model capable of performing the required reasoning tasks at acceptable accuracy — based on POC testing, not assumption?
6 | Does the organization have (or can it acquire) the skills to build, test, deploy, and maintain an agentic system?
7 | Can the agent's behavior be logged, traced, and audited at every step — input, reasoning, and action?
8 | Is there a viable path to handle failure modes — graceful degradation, human fallback, and error notification?
9 | Can the solution be deployed in an environment meeting the organization's security, privacy, and data residency requirements?
10 | Has a proof of concept or spike been conducted that demonstrates the core capability works for this specific task?
11 | Is the agent's architecture designed to handle production-scale volume and concurrency without degradation?
12 | Has the token consumption and LLM API cost been modeled at production volume, including retries and multi-step reasoning chains?
| D3 DIMENSION AVERAGE | —
D4: Risk, Governance & Compliance (Weight: 15%)
What could go wrong, how bad would it be, and can the organization manage those risks acceptably?
Rubric: 1=High-risk domain; irreversible actions; sensitive data; heavy regulation; no governance framework ¦ 2=Significant risk; some irreversible actions; regulatory constraints; governance immature ¦ 3=Moderate risk; most actions reversible; standard data handling; governance exists but needs extension ¦ 4=Low risk; actions reversible or low-impact; no sensitive data; governance covers this ¦ 5=Minimal risk; internal-only; non-sensitive; fully reversible; strong governance and kill-switch
1 | If the agent makes an incorrect decision, what is the worst-case business impact — and is that impact reversible?
2 | Does the use case involve sensitive data (PII, PHI, financial, confidential) that introduces regulatory obligations or breach risk?
3 | Are there regulatory or compliance requirements (SOX, HIPAA, GDPR, industry-specific) that constrain how an autonomous agent can operate?
4 | Can the agent's decisions be explained to a regulator, auditor, customer, or executive — or is it a black box?
5 | Is there a clear escalation path when the agent encounters an edge case, ambiguous situation, or ethical gray area?
6 | Has a threat model been developed that considers adversarial inputs, prompt injection, data poisoning, and misuse of the agent's tool access?
7 | Are the agent's access permissions scoped to the minimum necessary — or does it require broad access creating a large blast radius?
8 | Is there an established AI governance framework, ethics review, or responsible AI policy that this use case can be evaluated under?
9 | Can the agent be shut down, paused, or rolled back instantly if something goes wrong in production?
10 | Has legal counsel reviewed the liability implications of autonomous agent decisions in this domain?
11 | Is there a data lineage and provenance trail so the source of every input the agent uses can be traced?
| D4 DIMENSION AVERAGE | —
D5: Financial Viability (Weight: 15%)
Does the math work? Will this use case generate enough measurable value to justify the investment — and can you prove it?
Rubric: 1=No financial analysis; costs unknown; value is anecdotal ¦ 2=Rough estimates only; ROI uncertain; payback exceeds 18 months ¦ 3=Reasonable cost model; ROI is positive but modest; payback 12–18 months ¦ 4=Solid financial model; clear ROI; payback 6–12 months; funding identified ¦ 5=Compelling ROI; payback under 6 months; hard savings dominant; budget approved
1 | Can the current cost of the process (labor, errors, delays, opportunity cost) be quantified with real data — not estimates?
2 | Has a total cost of ownership been estimated — including development, infrastructure, LLM API costs, integration, testing, and ongoing maintenance?
3 | Is the projected ROI positive within 12 months, and is the payback period acceptable to the business?
4 | Are the value drivers primarily hard savings (FTE reduction, error elimination) or soft savings (speed, satisfaction) — and does leadership value both?
5 | Is the LLM/API cost per transaction sustainable at production volume, and has it been modeled with realistic token estimates?
6 | Has the cost of NOT doing this been articulated (growing backlog, competitive erosion, compliance risk)?
7 | Is there a funding mechanism identified (existing budget, new investment, shared services chargeback)?
8 | Have ongoing operational costs (monitoring, tuning, human-in-the-loop, model updates) been included in the TCO — not just build costs?
| D5 DIMENSION AVERAGE | —
D6: Organizational Readiness & Change Impact (Weight: 10%)
Even if the technology works and the math checks out, is the organization prepared to adopt, support, and sustain this?
Rubric: 1=No change plan; workforce resistance expected; single-team initiative; no operating model ¦ 2=Awareness of change need but no plan; limited stakeholder engagement; unclear ownership ¦ 3=Change plan in development; key stakeholders engaged; operating model being defined ¦ 4=Change plan in place; broad alignment; operating model defined; workforce impact addressed ¦ 5=Organization is change-ready; strong cross-functional support; operating model proven; workforce plan executed
1 | Will the people currently doing this work see the agent as a threat or as a relief — and has that been assessed honestly?
2 | Is there a change management plan that addresses communication, training, role redefinition, and transition timelines?
3 | Do the teams who will work alongside or supervise the agent trust AI outputs enough to rely on them?
4 | Is there a clear operating model for who owns the agent in production — monitoring, tuning, incident response, version updates?
5 | Has the organization successfully adopted a comparable technology change in the past 12 months?
6 | Are the right cross-functional stakeholders (IT, business, legal, compliance, HR) engaged and aligned?
7 | Is there a defined plan for what happens to the people whose work the agent takes over — redeployment, reskilling, or natural attrition?
8 | Is there a plan for sustained model and prompt maintenance — including monitoring for quality degradation and drift over time?
| D6 DIMENSION AVERAGE | —

## Hard Gates
HARD GATES — PASS / FAIL (any single Fail = mandatory hold)
Gate | Gate Name | Condition | Result | Evidence / Notes
G1 | Executive Sponsor | A named executive sponsor with budget authority is committed.
G2 | Legal / Compliance Clearance | Legal or compliance has confirmed there is no prohibition on using an autonomous agent in this domain.
G3 | Reversibility / Human Override | The agent's actions can be reversed, or a human can intervene before irreversible actions are taken.
G4 | Data Access Is Lawful | The data the agent needs can be accessed without violating privacy laws, contracts, or internal policies.
G5 | Kill Switch Exists | The agent can be stopped immediately in production without cascading failures.
G6 | POC Evidence | A proof of concept or benchmark has demonstrated that the core AI capability works for this specific task.
G7 | Observability | Every action the agent takes can be logged, traced, and audited after the fact.
G8 | Liability Reviewed | Legal counsel has reviewed the liability implications of autonomous agent decisions in this domain.
GATE STATUS |  |  | INCOMPLETE

## Financial Model
FINANCIAL MODEL
CURRENT STATE — ANNUAL COST
| Cost Component | Annual Cost ($)
Labor — direct (FTEs × fully loaded cost)
Labor — supervision / management
Error / rework cost (error rate × volume × cost per error)
Delay / SLA penalty cost
Opportunity cost (revenue delayed or lost due to process speed)
Tool / system licensing attributable to this process
| TOTAL CURRENT ANNUAL COST | 0
AGENTIC SOLUTION — COST MODEL
| Cost Component | One-Time ($) | Annual Recurring ($)
Development (internal labor)
Development (external / vendor)
LLM API costs (tokens × price × volume)
Infrastructure (compute, hosting, storage)
Integration development
Testing and QA
Change management and training
Ongoing maintenance and tuning
Monitoring and observability tooling
Human-in-the-loop labor (review, escalation)
| TOTAL ONE-TIME INVESTMENT | 0
| TOTAL ANNUAL OPERATING COST |  | 0
ROI SUMMARY
| Metric | Value
| Total current annual cost | 0
| Total one-time investment | 0
| Total new annual operating cost | 0
| Net annual benefit (current cost minus new operating cost) | 0
| Payback period (months) | N/A
| Year 1 ROI | N/A
| 3-Year NPV (10% discount rate) | 0

## Success Criteria
SUCCESS CRITERIA — DEFINE BEFORE IMPLEMENTATION
QUANTITATIVE SUCCESS METRICS
| Metric | Current Baseline | Minimum Threshold | Target | Stretch Goal
Agent accuracy (% decisions matching expert)
Cycle time reduction (%)
Throughput increase (%)
Error / rework rate
Human intervention rate (% of cases)
Cost per transaction ($)
SLA compliance rate (%)
First-contact resolution rate (%)
QUALITATIVE SUCCESS CRITERIA
| Criterion | How Measured | Acceptable Outcome
| User trust and adoption | Survey / usage analytics | ≥ 70% of eligible users actively using within 60 days
| Stakeholder satisfaction | Sponsor and team feedback | Sponsor confirms value; no requests to shut down
| Operational stability | Incident count, unplanned interventions | Zero critical incidents in first 30 days
| Auditability | Audit team review | All agent actions traceable; audit confirms compliance
| Graceful failure | Edge case testing | 100% of edge cases route to human fallback
PILOT GUARDRAILS
| Guardrail | Specification
Pilot duration (days)
Pilot scope (team / region / transaction subset)
Volume cap (max transactions per day during pilot)
Human review rate — first 2 weeks (%)
Human review rate — weeks 3+ (%)
Rollback trigger (accuracy threshold for auto-pause)
Decision checkpoint dates

## Scorecard
SCORECARD — FEASIBILITY SUMMARY
Dimension | Weight | Avg Score | Weighted Score | Rating | Interpretation
D1: Strategic & Business Alignment | 25% | — | 0 | Not scored
D2: Process Readiness | 15% | — | 0 | Not scored
D3: Technical Feasibility | 20% | — | 0 | Not scored
D4: Risk, Governance & Compliance | 15% | — | 0 | Not scored
D5: Financial Viability | 15% | — | 0 | Not scored
D6: Organizational Readiness & Change Impact | 10% | — | 0 | Not scored
COMPOSITE FEASIBILITY SCORE |  |  | 0 | NO GO | Fundamental misalignment — do not pursue
HARD GATE STATUS |  |  | INCOMPLETE | HOLD — resolve failed gates before proceeding
FINANCIAL SUMMARY
Current annual cost | 0
One-time investment | 0
New annual operating cost | 0
Net annual benefit | 0
Payback period (months) | N/A
Year 1 ROI | N/A
PRIORITY ATTENTION AREAS (lowest-scoring dimensions)
Review the Assessment tab for the dimensions with the lowest average scores. Any dimension below 3.0 should have a mitigation plan before proceeding.
DECISION: NO GO — This use case has fundamental gaps. Do not invest. Redirect to higher-value opportunities.